МАТRIXGIN V2.0 — ПОЛНЫЙ ПЛАН РЕАЛИЗАЦИИ ПРОЕКТА И ЧЕКЛИСТ

- Дата: 21 ноября 2025

- Версия: 1.0

- Статус: READY FOR EXECUTION

- Автор: Экспертная команда MatrixGin

О СОДЕРЖАНИЕ

  - Обзор проекта и ключевые параметры

  - Структу ра проекта (WBS)

  - Фазы разработки (40-50 недель)

  - Команда проекта и роли

  - Риск-менеджмент

  - ПОЛНЫЙ ЧЕКЛИСТ РЕАЛИЗАЦИИ

  - Финансовые параметры

  - KPI и метрики у спеха

- ОБЗОР ПРОЕКТА И КЛЮЧЕВЫЕ ПАРАМЕТРЫ

  - Описание проекта

MatrixGin v2.0 — революционная интегрированная платформа управления предприятием с встроенным AI-ассистентом, реализующая философию Lean Production и Kaizen 2.0.

Уникальность:

□□ Полная адаптация для российского законодательства (152-ФЗ, ТК РФ, 54-ФЗ, НК РФ)

- Локальные LLM (Qwen, DeepSeek) вместо платных API (экономия $50,000+/год)

- Гибридная команда (Человек + AI) с Human Oversight Protocol

- Геймификация и система мотивации (MatrixCoin + GMC)

- Telegram Mini Apps как primary interface

  - Стратегические цели

| # | Цель | Как измерить | Целевое значение |
| --- | --- | --- | --- |
| 1 | Запустить MVP за 3-4 месяца | Дата запуска в production | 1 апреля 2026 |
| 2 | Внедрить на 2-3 пилотных клиентах | Кол-во активных клиентов | 3 |
| 3 | Достичь 80%+ user engagement | Weekly active users / Total users | >80% |
| 4 | Обеспечить 99.5% uptime | Downtime в месяц | <3.6 часов |
| 5 | Полное соответствие 152-ФЗ | Security audit results | Pass |
| 6 | Экономия на LLM API | Затраты на облачные LLM | $0-6,000/мес |

  - Ключевые параметры проекта

| Параметр | Значение |
| --- | --- |
| Продолжительность MVP | 12-16 недель (3-4 месяца) |
| Полная разработка | 40-50 недель (9-12 месяцев) |
| Размер команды | 10-12 человек (или 7-8 + аутсорс) |
| CAPEX | $390,000 (первый год) |
| OPEX | $72,000-240,000 (первый год) |
| Целевые клиенты | Малый/средний бизнес 50-5,000 сотрудников |
| Запуск пилота | Q2 2026 (май-июнь) |
| Break-even | Месяц 18 (май 2027) при 30 клиентах |
| Целевое значение ARR Год 3 | $1,800,000 |

- СТРУКТУРА ПРОЕКТА (WBS)

  - Иерархия работ

MatrixGin v2.0

│

├── ФАЗА 0: INFRASTRUCTURE &amp; SETUP (Недели 1-2)

│	├── Инфраструктура (Cloud, VPS)

│	├── CI/CD pipelines (GitHub Actions)

│	├── Database setup (PostgreSQL, Redis, Qdrant)

│	├── Мониторинг и логирование (Prometheus, ELK)

│	└── Dev &amp; staging окружения

│

├── ФАЗА 1: MVP FOUNDATION (Недели 3-8)

│	├── Backend core (Nest.js, Authentication)

│	├── Database schema (Users, Tasks, KPI)

│	├── Frontend core (React 18, Tailwind CSS)

│	├── Telegram Bot (базовые команды)

│	├── Authorization &amp; RBAC

│	└── API endpoints (первый набор)

│

├── ФАЗА 2: CORE MODULES (Недели 9-14)

│	├── Employee Management (CRUD, структура)

│	├── Task Management (создание, назначение, статусы)

│	├── KPI &amp; Analytics (персональные KPI, дашборды)

│	├── MatrixCoin Economy (базовая система)

│	├── Legal Compliance (152-ФЗ базовая)

│	└── Gamification (статусы, достижения)

│

├── ФАЗА 3: MVP LAUNCH (Недели 15-16)

│	├── QA &amp; тестирование

│	├── Security audit

│	├── Deployment на production

│	├── Документация

│	└── Запуск пилота (1-2 клиента)

│

├── ФАЗА 2+ (Месяцы 5-12): EXTENDED FEATURES

│	├── Emotional Analytics

│	├── HR Analytics (Matrix360)

│	├── RAG System

│	├── ERP-модули (Закупки, Склад, Бюджет, ОС)

│	├── Production Management

│	└── Advanced features

│

└── ОПЕРАЦИОННАЯ ПОДДЕРЖКА (Параллельно)

├── Go-to-market

├── Sales &amp; Marketing

├── Customer support

└── Привлечение инвестиций

  - Основные вехи проекта (Milestones)

| # | Веха | Дата | Зависит от |
| --- | --- | --- | --- |
| M1 | Инфраструктура ready | Неделя 2 | Подбор хостинга |
| M2 | Backend + auth working | Неделя 8 | Дизайн БД |
| M3 | Frontend + Telegram Bot | Неделя 8 | React setup |
| M4 | Core modules 70% ready | Неделя 14 | M2 + M3 |
| M5 | MVP release на staging | Неделя 15 | Все модули |
| M6 | Security audit passed | Неделя 16 | Pентест |
| M7 | MVP в production | Неделя 17 (апрель 2026) | M6 |
| M8 | Пилот-клиент #1 active | Неделя 20 | M7 + onboarding |
| M9 | Feedback собран | Неделя 24 | 2 недели использования |

- ФАЗЫ РАЗРАБОТКИ (40-50 НЕДЕЛЬ)

  - ФАЗА 0: INFRASTRUCTURE & SETUP (Недели 1-2)

Цель: Подготовить полную инфраструктуру для разработки и production.

    - Выбор хостинга и облака

Опции:

      - Selectel (российский провайдер, 152-ФЗ compliant)  VPS: 2 CPU, 8GB RAM — $50/месяц

GPU A100 40GB — $2,000-3,000/месяц

Преимущества: локальное, compliance, низкие задержки

      - Yandex.Cloud (российский)

VM Instance (n1-standard-2) — $40-50/месяц  GPU (V100/L4) — $1,000-2,000/месяц

Плюсы: интеграция с YandexGPT, данные в РФ

      - DigitalOcean (если разрешено)  Droplet 8GB — $48/месяц

Kubernetes — $100-200/месяц

Выбор: Selectel (Russian-first, 152-ФЗ ready)

    - Docker & Containerization Setup

Задачи:

[ ] Инициализировать Docker repository на GitHub [ ] Создать Dockerfiles для:

[ ] Backend (Node.js)  [ ] Python ML services

[ ] PostgreSQL + Redis  [ ] Nginx reverse proxy

[ ] Написать docker-compose.yml для локальной разработки [ ] Протестировать запуск локально

    - CI/CD Pipeline (GitHub Actions)

Workflow:

events:

- on: push to main/develop steps:

  - Checkout code

  - Run linter (ESLint, Prettier)

  - Build Docker image

  - Run unit tests (Jest)

  - Run integration tests

  - Build frontend (Vite)

  - Push to Docker registry

  - Deploy to staging

  - Run E2E tests

  - Merge to main → Deploy to production

Задачи:

[ ] Создать .github/workflows/ci-cd.yml

[ ] Настроить Docker registry (Selectel Registry или GitHub Container Registry)  [ ] Настроить staging & production environments

[ ] Настроить notifications (Slack/Telegram)

    - Database Setup

PostgreSQL:

[ ] Инстанс PostgreSQL 16 на Selectel  [ ] Инициальная схема (schema.sql)

[ ] Backup стратегия (ежедневные в S3)  [ ] Миграции (using Prisma Migrate)

Redis:

[ ] Инстанс Redis 7

[ ] Конфигурация persistence (RDB)  [ ] Cluster mode (опционально)

Qdrant (Vector DB):

[ ] Docker container Qdrant

[ ] Collection config для embeddings

S3 (MinIO или Selectel S3):

[ ] Bucket для документов, логов

[ ] Lifecycle rules (архивирование через 30 дней)

    - Monitoring & Logging

Prometheus:

[ ] Scrape config для Node.js, PostgreSQL, Redis

[ ] Alarms (CPU > 80%, Disk > 90%, DB slow queries)

Grafana:

[ ] Dashboards (System, Application, Database)  [ ] Alert notifications (Slack)

ELK Stack (или Loki):

[ ] Log aggregation setup

[ ] Indexes для разных компонентов  [ ] Retention: 30 дней

Sentry (для error tracking):

[ ] Initialize Sentry project

[ ] Configure DSN в backend & frontend  [ ] Setup slack notifications

    - Development Environments

Локальный dev:

[ ] .env.example для переменных окружения  [ ] Инструкция по запуску (README)

[ ] Pre-commit hooks (линтинг)

Staging:

[ ] Отдельный PostgreSQL, Redis (на Selectel)  [ ] Копия production конфига

[ ] Автоматические E2E тесты

Production:

[ ] HA setup (load balancer, replicas)  [ ] DDoS protection

[ ] WAF (Web Application Firewall)  [ ] SSL/TLS с Let's Encrypt

Ответственный: DevOps Engineer

Время: 5-7 дней

Бюджет: $1,000-2,000 (setup + месячная подписка)

  - ФАЗА 1: MVP FOUNDATION (Недели 3-8)

Цель: Реализовать backend core, authentication, basic frontend и Telegram Bot.

    - Backend Architecture & Setup

Nest.js структура:

src/

├── main.ts

├── app.module.ts

├── config/

│	├── database.config.ts

│	├── jwt.config.ts

│	└── env.validation.ts

├── auth/

│	├── auth.service.ts

│	├── auth.controller.ts

│	├── jwt.strategy.ts

│	├── rbac.guard.ts

│	└── entities/

├── users/

│	├── users.service.ts

│	├── users.controller.ts

│	├── dto/

│	└── entities/

├── common/

│	├── filters/

│	├── pipes/

│	├── decorators/

│	└── exceptions/

└── database/

├── prisma.service.ts

└── migrations/

Задачи:

[ ] Инициализировать Nest.js проект с Typescript  [ ] Настроить Prisma ORM (schema.prisma)

[ ] Создать базовую структуру модулей  [ ] Setup error handling & logging

[ ] Конфигурация переменных окружения (.env)

    - Database Schema (Phase 1)

Критичные таблицы:

-- Users &amp; Auth CREATE TABLE users (

id UUID PRIMARY KEY,

email VARCHAR(255) UNIQUE,

password_hash VARCHAR(255), first_name VARCHAR(100), last_name VARCHAR(100),

role_id UUID REFERENCES roles(id), status VARCHAR(50), -- active, inactive created_at TIMESTAMPTZ,

updated_at TIMESTAMPTZ

);

-- Tasks

CREATE TABLE tasks (

id UUID PRIMARY KEY, title VARCHAR(255),

description TEXT,

creator_id UUID REFERENCES users(id), assignee_id UUID REFERENCES users(id),

status VARCHAR(50), -- new, in_progress, completed priority VARCHAR(20), -- low, medium, high created_at TIMESTAMPTZ,

completed_at TIMESTAMPTZ

);

-- KPI

CREATE TABLE kpi (

id UUID PRIMARY KEY,

user_id UUID REFERENCES users(id), metric_name VARCHAR(100), target_value DECIMAL, current_value DECIMAL,

period DATE, created_at TIMESTAMPTZ

);

-- Event Log

CREATE TABLE event_log ( id UUID PRIMARY KEY,

event_type VARCHAR(50), entity_type VARCHAR(50), entity_id UUID,

actor_id UUID REFERENCES users(id), timestamp TIMESTAMPTZ,

metadata JSONB

);

-- Departments

CREATE TABLE departments ( id UUID PRIMARY KEY, name VARCHAR(100),

parent_id UUID REFERENCES departments(id), created_at TIMESTAMPTZ

);

-- MatrixCoin

CREATE TABLE matrixcoin ( id UUID PRIMARY KEY,

user_id UUID REFERENCES users(id),

balance DECIMAL,

type VARCHAR(20), -- MC or GMC

created_at TIMESTAMPTZ, updated_at TIMESTAMPTZ

);

Задачи:

[ ] Определить Prisma schema

[ ] Миграция БД (prisma migrate dev)

[ ] Seed script для dev данных (200 пользователей, 500 задач)

    - Authentication & Authorization

JWT Implementation:

// auth.service.ts

async login(email: string, password: string): Promise&lt;JwtPayload&gt; { const user = await this.usersService.findByEmail(email);

const isValid = await bcrypt.compare(password, user.password_hash);

if (!isValid) throw new UnauthorizedException();

const payload = { sub: user.id, email: user.email, role: user.role }; return { access_token: this.jwtService.sign(payload) };

}

RBAC Middleware:

[ ] Guard для проверки ролей (@Roles decorator)  [ ] Permissions mapping (Role → Actions)

[ ] Audit logging для всех действий

Задачи:

[ ] Реализовать JWT auth (Passport.js)  [ ] Создать RBAC систему

[ ] Защитить все API endpoints  [ ] Тестирование auth flow

    - Frontend Setup (React 18)

Структура:

frontend/

├── src/

│	├── main.tsx

│	├── App.tsx

│	├── pages/

│	│	├── Login.tsx

│	│	├── Dashboard.tsx

│	│	├── Tasks.tsx

│	│	└── Settings.tsx

│	├── components/

│	│	├── Header.tsx

│	│	├── Sidebar.tsx

│	│	├── TaskCard.tsx

│	│	└── KpiDisplay.tsx

│	├── hooks/

│	│	├── useAuth.ts

│	│	├── useTasks.ts

│	│	└── useApi.ts

│	├── store/

│	│	└── store.ts (Redux Toolkit)

│	└── styles/

│	└── globals.css (Tailwind)

├── public/

└── vite.config.ts

Задачи:

[ ] Инициализировать Vite + React 18 + Typescript  [ ] Setup Tailwind CSS

[ ] Setup Redux Toolkit + RTK Query

[ ] Создать основные страницы (Login, Dashboard)  [ ] Дизайн компонентов по Figma

    - Telegram Bot Integration (MVP)

Telegram Mini Apps (TMA):

// telegramBot.service.ts

async handleCommand(message: Update): Promise&lt;void&gt; { if (message.message?.text === '/start') {

// Отправить приветствие + ссылку на web app const webAppButton = {

text: 'Открыть MatrixGin',

web_app: { url: 'https://matrixgin.app' }

};

}

if (message.message?.text?.startsWith('/tasks')) {

// Получить задачи пользователя

const tasks = await this.tasksService.getUserTasks(userId);

// Форматировать и отправить

}

}

Базовые команды:

/start — Приветствие + ссылка на web app

/tasks — Мои задачи

/status — Мой статус/KPI

/help — Справка

Задачи:

[ ] Setup Telegram Bot на BotFather

[ ] Разработать Telegram Mini App (WebView)  [ ] Интеграция с backend API

[ ] Тестирование базовых команд

    - API Endpoints (Phase 1)

Реализовать 20-25 основных эндпоинтов: Auth:

[ ] POST /api/auth/register  [ ] POST /api/auth/login

[ ] POST /api/auth/logout  [ ] POST /api/auth/refresh

Users:

[ ] GET /api/users

[ ] GET /api/users/{id}  [ ] POST /api/users

[ ] PUT /api/users/{id}

[ ] PATCH /api/users/{id}

[ ] DELETE /api/users/{id}

Tasks:

[ ] GET /api/tasks

[ ] GET /api/tasks/{id}  [ ] POST /api/tasks

[ ] PUT /api/tasks/{id}

[ ] DELETE /api/tasks/{id}

[ ] POST /api/tasks/{id}/assign

[ ] POST /api/tasks/{id}/complete

KPI:

[ ] GET /api/kpi

[ ] GET /api/kpi/{userId}  [ ] POST /api/kpi

Departments:

[ ] GET /api/departments

[ ] POST /api/departments

MatrixCoin:

[ ] GET /api/economy/balance/{userId}  [ ] GET /api/economy/transactions

Ответственный: Senior Backend Developer + Frontend Developer

Время: 16-20 дней

Результат: Работающий MVP с authentication, базовой функциональностью

  - ФАЗА 2: CORE MODULES (Недели 9-14)

Цель: Реализовать 7 критичных модулей для MVP.

Модуль 1: Employee Management

Функции:

CRUD сотрудников

Организационная структура (иерархия отделов)  Должности и ранги

Статусы сотрудников

Задачи:

[ ] Расширить users table (department_id, position, rank)  [ ] API для управления структурой

[ ] Дашборд HR (список сотрудников)  [ ] Экспорт в CSV/Excel

[ ] Интеграция с 1С (отложено на Phase 2)

Время: 4-5 дней

Модуль 2: Task Management (Smart)

Функции:

Создание задач (форма + NLP) Автоназначение (по MDR или волонтеры)

Статусы и workflow  Комментарии

Уведомления

Задачи:

[ ] Расширить tasks table (comments, attachments, watchers)  [ ] Websocket для real-time updates

[ ] NLP парсинг (отложено, сейчас простая форма)  [ ] Notification engine (email, Telegram)

[ ] Task filtering & search

Время: 5-6 дней

Модуль 3: KPI & Analytics (Basic)

Функции:

Персональные KPI  Дашборд прогресса

Простые отчеты (PDF)  Графики выполнения

Задачи:

[ ] Дизайн KPI структуры (таблица kpi_snapshots)  [ ] Автоматический расчет прогресса

[ ] Дашборд для сотрудников

[ ] Дашборд для менеджеров (команды)  [ ] Charts (Recharts + Chart.js)

Время: 4-5 дней

Модуль 4: MatrixCoin Economy (Basic)

Функции:

Кошельки (MC + GMC)  Транзакции (переводы)  История операций

Простой магазин (опционально)

Задачи:

[ ] Таблицы: wallets, transactions

[ ] API для операций (с валидацией баланса)

[ ] Начисление MC за выполненные задачи (+10 MC)  [ ] Дашборд кошелька

[ ] История транзакций

Время: 3-4 дня

Модуль 5: Legal Compliance (Base)

Функции:

Базовая 152-ФЗ (согласия)  Audit log

NDA при регистрации  Простой checklist

Задачи:

[ ] Таблицы: compliance_log, nda_records  [ ] API для управления согласиями

[ ] Генерация NDA текста

[ ] Tracking принятия документов  [ ] Простой compliance dashboard

Время: 3-4 дня

Модуль 6: Telegram Bot Integration (Extended)

Функции:

Расширенные команды

Создание задач через бот  Уведомления

Статус пользователя

Команды:

/start — Приветствие

/tasks — Мои задачи

/status — Мой статус &amp; баланс

/create — Создать задачу (форма)

/complete — Отметить задачу (выбор)

/help — Справка

Задачи:

[ ] Разработать conversational interface [ ] Middleware для auth (через token)

[ ] Обработка inline buttons

[ ] Интеграция с основным API

[ ] Тестирование на 100+ пользователях

Время: 4-5 дней

Модуль 7: Gamification (Base)

Функции:

Статусы (5 уровней: Фотон, Топчик, Кремень, Углерод, UNIVERSE)  Простые достижения

Лидерборд

Автоматический расчет статуса

Задачи:

[ ] Таблицы: statuses, achievements, leaderboard (view)  [ ] Cron job для ежедневного пересчета статуса

[ ] API для получения статуса & привилегий  [ ] Дашборд лидерборда

[ ] Upgrade ceremony notifications

Время: 3-4 дня

Ответственный: 2-3 backend разработчика + 1-2 frontend разработчика

Время: 21-28 дней

Результат: 7 полностью функциональных модулей

  - ФАЗА 3: MVP LAUNCH & TESTING (Недели 15-16)

Цель: Протестировать, исправить баги, запустить в production.

    - Quality Assurance

Unit тестирование:

[ ] Все services имеют unit tests (Jest)  [ ] Coverage > 70%

[ ] Запуск автоматически в CI/CD

Integration тестирование:

[ ] API endpoint tests (Supertest) [ ] Database interactions

[ ] Auth flow

E2E тестирование:

[ ] Критичные user flows (login → create task → complete)  [ ] Telegram Bot команды

[ ] Payment flow (если есть)

[ ] Инструмент: Playwright или Cypress

Performance тестирование:

[ ] Load testing (k6)

[ ] Целевой: <500ms на основные запросы  [ ] Concurrent users: 100+

Задачи:

[ ] Написать test plans для каждого модуля

[ ] Выполнить manual testing (QA team 2-3 человека)  [ ] Автоматические tests в CI/CD

[ ] Performance profiling (Node.js profiler)  [ ] Memory leak detection

    - Security Audit & Penetration Testing

Внутренний аудит:

[ ] JWT token security

[ ] SQL injection prevention (Prisma ORM защищен)  [ ] CSRF protection

[ ] XSS prevention

[ ] CORS configuration  [ ] Rate limiting

Проверки:

[ ] OWASP Top 10

[ ] Dependency vulnerabilities (npm audit, Snyk)  [ ] SSL/TLS configuration

[ ] Database encryption

Пентест (внешняя компания):

[ ] Контрактор: Security company [ ] Стоимость: $3,000-5,000

[ ] Результат: Report с рекомендациями

[ ] Исправление критичных уязвимостей

Задачи:

[ ] Провести внутренний аудит

[ ] Заказать пентест (параллельно с разработкой)  [ ] Исправить найденные проблемы

[ ] Получить security certificate

    - Documentation

Техническая документация:

[ ] API Documentation (OpenAPI/Swagger)  [ ] Database Schema (EER diagram)

[ ] Architecture Decision Records (ADR)  [ ] Deployment guide

[ ] Troubleshooting guide

Пользовательская документация:

[ ] User manual (PDF, 10-15 страниц)

[ ] Video tutorials (3-5 видео по 5-10 минут)  [ ] FAQ

Developer documentation:

[ ] Setup guide (README)  [ ] Code style guide

[ ] Contribution guidelines  [ ] Git workflow

Задачи:

[ ] Создать Confluence/Notion wiki

[ ] Swagger UI для API (автогенерируется)  [ ] Записать видео туториалы (Loom)

[ ] Подготовить onboarding материалы

    - Production Deployment

Pre-deployment чеклист:

[ ] Все тесты passed (100%) [ ] Security audit completed

[ ] Database backups working

[ ] Monitoring configured  [ ] Rollback plan ready

[ ] Communication plan для stakeholders

Deployment процесс:

- Freeze на new features (24 часа до релиза)

- Final testing на staging

- Backup production database

- Blue-green deployment (параллельная версия)

- Health checks (API, Database, services)

- Smoke tests на production

- Gradual traffic shift (10% → 50% → 100%)

- Monitoring escalation

Задачи:

[ ] Подготовить production servers  [ ] Миграции БД (production)

[ ] Настроить SSL/TLS certificates  [ ] Финальное тестирование

[ ] Запуск deployment скрипта

[ ] Мониторинг 24/7 в первые 48 часов

Время: 7-10 дней (параллельно с Phase 2)

Результат: MVP v1.0 в production с нулевыми инцидентами

  - PHASE 2+ (Месяцы 5-12): EXTENDED FEATURES

После успешного запуска MVP и сбора feedback от пилот-клиентов:

Месяцы 5-8 (Phase 2):

Psychological Support & Emotional Analytics  HR Analytics (Matrix360)

Learning & Corporate University

Advanced Gamification (GMC, Auctions)  RAG System & Knowledge Base

Месяцы 9-12 (Phase 3):

Критичные ERP-модули (Procurement, WMS, Budgeting, Fixed Assets) Production Management (MES, Quality)

Content Factory Executive Dashboard

Advanced Analytics & Predictions

- КОМАНДА ПРОЕКТА И РОЛИ

  - Структура команды (10-12 человек)

| # | Роль | Кол-во | Опыт | Зарплата/мес | Примечание |
| --- | --- | --- | --- | --- | --- |
| 1 | Product Manager | 1 | 5-7 лет | $2,500-3,500 | Vision & priorities |
| 2 | Tech Lead/Architect | 1 | 8-10 лет | $3,500-5,000 | System design |
| 3 | Senior Backend Dev | 2 | 5-7 лет | $2,500-3,500 | Core services |
| 4 | Backend Dev (Middle) | 2 | 3-5 лет | $1,500-2,500 | API development |
| 5 | Frontend Lead | 1 | 5-7 лет | $2,500-3,500 | UI/UX & design |
| 6 | Frontend Dev | 1 | 3-5 лет | $1,500-2,500 | React components |
| 7 | QA/Test Engineer | 1 | 3-5 лет | $1,200-2,000 | Тестирование |
| 8 | DevOps Engineer | 1 | 3-5 лет | $2,000-3,000 | Инфра & CI/CD |
| 9 | ML/LLM Specialist | 1 | 3-5 лет | $2,000-3,000 | Local LLM setup |
| 10 | Telegram Bot Dev (part-time) | 1 | 2-3 года | $800-1,200 | Bot integration |
| 11 | Security/Compliance Officer (part-time) | 1 | 5-7 лет | $1,500-2,500 | 152-ФЗ audit |

Итого: $20,600-32,720 месячно (разработка + поддержка)

За 40-50 недель (9-12 месяцев): $185,400-393,840

  - Распределение ответственности

| Компонент | Владелец | Backup |
| --- | --- | --- |
| Backend Architecture | Tech Lead | Senior Backend Dev |
| Frontend Architecture | Frontend Lead | Senior Backend Dev |
| Database Design | Tech Lead | Backend Dev (Middle) |
| API Endpoints | Senior Backend Dev + Middle | Backend Dev (Middle) |
| React Components | Frontend Lead + Frontend Dev | Frontend Lead |
| Telegram Bot | Telegram Bot Dev | Senior Backend Dev |
| Testing Strategy | QA Engineer | Tech Lead |
| Deployment & CI/CD | DevOps Engineer | Tech Lead |
| LLM Integration | ML Specialist | Senior Backend Dev |
| Security & Compliance | Security Officer | Tech Lead |
| Product Vision | Product Manager | Tech Lead |

  - Communication & Meetings

Daily:

15:00 — Daily standup (15 минут, каждый день)

Weekly:

Понедельник 10:00 — Sprint planning (1 час)  Среда 14:00 — Technical sync (1 час)

Пятница 16:00 — Sprint retro (1 час)

Ad-hoc:

Code reviews (во время разработки)

Emergency calls (при критичных багах)

- РИСК-МЕНЕДЖМЕНТ

  - Основные риски и стратегии снижения

| # | Риск | Вероятность | Влияние | Стратегия снижения |
| --- | --- | --- | --- | --- |
| 1 | Задержка на месяц+ | Средняя | Высокое | MVP из 5 модулей (вместо 7), параллельная разработка |
| 2 | Утечка данных 152-ФЗ | Низкая | Критичное | Пентест в week 8, encryption AES-256, audit logs |
| 3 | LLM API dependency | Средняя | Среднее | Локальные LLM как основа, fallback стратегия |
| 4 | Уход ключевого разработчика | Низкая | Высокое | Документирование, парное программирование |
| 5 | Performance issues на production | Средняя | Среднее | Load testing (k6), database indexing, caching strategy |
| 6 | Пилот-клиент не доволен | Средняя | Высокое | Еженедельные review, быстрое исправление багов, support 24/5 |
| 7 | Несовместимость с 1С | Средняя | Среднее | Тестирование интеграции на week 6, backup API approach |

  - Risk Register (Детальный)

Risk #1: Задержка разработки

Причины: Scope creep, недооценка сложности, technical blockers Индикаторы: Более 3 tasks не завершено к концу спринта Ответственный: Tech Lead + Product Manager

План B: Reduce scope (убрать 2-3 низкоприоритетных модуля)

Risk #2: Безопасность 152-ФЗ

Причины: Неполное понимание требований, недостаточный аудит

Индикаторы: Security review находит критичные findings

Ответственный: Security Officer

План B: Отложить production на 2 недели, провести полный audit

Risk #3: LLM затраты выше бюджета

Причины: Неопределенный API consumption, low inference efficiency

Индикаторы: Счета за API > $2,000/месяц

Ответственный: ML Specialist + DevOps

План B: Переключиться на полностью локальные LLM (может потребоваться замедление ответов)

- ПОЛНЫЙ ЧЕКЛИСТ РЕАЛИЗАЦИИ

  - ФАЗА 0 CHECKLIST (Недели 1-2)

Инфраструктура

[ ] Выбран хостинг-провайдер (Selectel)  [ ] Зарегистрирован аккаунт

[ ] Выбрана тарифный план (VPS 8GB RAM, $50/месяц)  [ ] SSH ключи сгенерированы

[ ] Сервер ready (IP, hostname) [ ] Регионы и DPA (152-ФЗ)

[ ] Сервер в России (Selectel Москва)

[ ] Data Processing Agreement подписан с провайдером  [ ] Документирование place of data storage

[ ] Docker & Containerization

[ ] Docker installed на сервере  [ ] Docker Compose configured

[ ] Dockerfile для Node.js написан  [ ] Dockerfile для Python написан  [ ] Dockerfile для Nginx написан

[ ] docker-compose.yml для dev написан  [ ] Локальный docker setup тестирован

[ ] GitHub Repository Setup

[ ] Репо создано (matrixgin-backend, matrixgin-frontend)  [ ] .gitignore configured

[ ] Protected branches (main, develop)  [ ] Collaborators добавлены

[ ] Branch protection rules:

[ ] Require 2 code reviews

[ ] Require passing CI/CD checks [ ] CI/CD Pipeline (GitHub Actions)

[ ] .github/workflows/ci-cd.yml создан  [ ] Workflow triggered on push/PR

[ ] Stages:

[ ] Lint (ESLint, Prettier)  [ ] Unit tests (Jest)

[ ] Build Docker image  [ ] Push to registry

[ ] Deploy to staging  [ ] E2E tests

[ ] Slack notifications configured [ ] Database Infrastructure

[ ] PostgreSQL 16 instance на Selectel  [ ] Connection string добавлен в .env

[ ] Backup стратегия (ежедневно в S3)  [ ] Retention: 30 дней

[ ] SSH tunnel для локального подключения [ ] Redis Setup

[ ] Redis instance deployed  [ ] RDB persistence enabled

[ ] Memory limit configured (8GB)  [ ] Password set

[ ] Qdrant Vector DB

[ ] Docker контейнер запущен  [ ] Port mapped (6333)

[ ] Collection schema подготовлена (для Phase 2) [ ] S3 Storage (MinIO/Selectel)

[ ] S3 bucket создан (documents, logs)

[ ] Access keys generated

[ ] Lifecycle rules: archive after 30 days  [ ] Monitoring & Logging

[ ] Prometheus deployed (на VM или cloud)

[ ] Scrape configs для Node.js, PostgreSQL, Redis  [ ] Alarms configured (CPU, Disk, DB slow queries)  [ ] Grafana dashboards created (System, App, DB)  [ ] ELK Stack deployed (или Loki)

[ ] Log aggregation working  [ ] Sentry project created

[ ] DSN integrated в backend & frontend  [ ] SSL/TLS & Security

[ ] SSL certificate ordered (Let's Encrypt)  [ ] Nginx reverse proxy configured

[ ] HTTPS enforced

[ ] Security headers added (HSTS, CSP, X-Frame-Options)  [ ] WAF rules configured (DDoS protection)

[ ] Development Environment

[ ] .env.example template created  [ ] Dev setup guide написан

[ ] Pre-commit hooks configured (husky)

[ ] IDE extensions recommended (VSCode)  [ ] README updated

Документирование

[ ] Infra documentation создана (Confluence/Notion)  [ ] Access management documented (who has what)  [ ] Disaster recovery plan written

Signoff: DevOps Engineer, Tech Lead

Status: □ In Progress

  - ФАЗА 1 CHECKLIST (Недели 3-8)

Backend Foundation

[ ] Nest.js Setup

[ ] Project initialized (npm install)

[ ] TypeScript configured (tsconfig.json)  [ ] @nestjs/cli installed

[ ] Main modules created (AppModule, etc.)  [ ] Main.ts configured

[ ] Database Connection

[ ] Prisma ORM initialized

[ ] Prisma schema drafted (initial tables)  [ ] Database migrations working

[ ] Seed script for dev data

[ ] Connection pooling configured  [ ] Authentication (JWT)

[ ] @nestjs/jwt installed

[ ] Passport.js with JWT strategy  [ ] auth.controller.ts created

[ ] auth.service.ts with login/register

[ ] Password hashing (bcrypt) working

[ ] JWT tokens generated (15 min expiry)  [ ] Refresh tokens implemented (7 days)

[ ] JWT stored securely (httpOnly cookies)  [ ] Tests written for auth flow

[ ] Authorization (RBAC)

[ ] roles table in database

[ ] Roles defined (Admin, Manager, Employee, Bot)  [ ] @Roles() decorator created

[ ] RolesGuard middleware

[ ] Routes protected with @Roles  [ ] Unit tests for RBAC

[ ] Error Handling

[ ] ExceptionFilter for HTTP errors  [ ] Custom exception classes

[ ] Error responses formatted standardly  [ ] Logging errors with stack trace

[ ] 404, 400, 401, 403, 500 handled

[ ] Logging

[ ] Winston logger configured  [ ] Logs to console + file

[ ] Log levels: debug, info, warn, error  [ ] Request logging middleware

[ ] Performance logging  [ ] API Documentation

[ ] @nestjs/swagger installed

[ ] Swagger decorators on endpoints  [ ] Swagger UI at /api/docs

[ ] All endpoints documented

Database Schema (Phase 1)

[ ] Core Tables

[ ] users table (id, email, password_hash, first_name, last_name, role_id, status, created_at)  [ ] roles table (id, name, permissions JSONB)

[ ] tasks table (id, title, description, creator_id, assignee_id, status, priority, created_at, completed_at)

[ ] kpi table (id, user_id, metric_name, target, current, period)  [ ] departments table (id, name, parent_id)

[ ] matrixcoin table (id, user_id, balance, type (MC/GMC))

[ ] event_log table (id, event_type, entity_type, entity_id, actor_id, timestamp, metadata JSONB)

[ ] compliance_log table (id, user_id, action, timestamp) [ ] Migrations & Seeds

[ ] Migration files created

[ ] Initial schema migrated to dev DB  [ ] Seed script creates:

[ ] 5 roles (Admin, HR, Manager, Employee, Bot)  [ ] 100+ users (test@example.com, etc.)

[ ] 10 departments

[ ] 500 tasks (various statuses)

[ ] Sample KPI data

[ ] Seed script tested on clean DB

Frontend (React 18)

[ ] Project Setup

[ ] Vite + React 18 + TypeScript  [ ] package.json dependencies  [ ] tsconfig.json proper

[ ] vite.config.ts configured  [ ] ESLint + Prettier setup

[ ] Styling

[ ] Tailwind CSS installed  [ ] tailwind.config.js

[ ] CSS reset applied

[ ] Color scheme defined (use design system from Architecture doc)  [ ] Responsive utilities (sm, md, lg breakpoints)

[ ] State Management

[ ] Redux Toolkit configured

[ ] RTK Query setup (@reduxjs/toolkit/query)  [ ] Base query with auth header

[ ] Store persisted (localStorage for tokens) [ ] Pages & Components

[ ] Layout component (Header, Sidebar, Main)  [ ] Login page (email/password form)

[ ] Dashboard page (skeleton)

[ ] Tasks page (list + create form)  [ ] Settings page (profile, logout)  [ ] 404 page

[ ] Hooks & Utilities

[ ] useAuth hook (login, logout, currentUser)  [ ] useApi hook (API calls with error handling)

[ ] useTasks hook (getTasks, createTask, updateTask)  [ ] useLocalStorage hook (for token persistence)

[ ] Form Handling

[ ] React Hook Form installed

[ ] Zod for schema validation  [ ] Login form with validation  [ ] Task creation form

[ ] Error messages displayed  [ ] API Integration

[ ] API client configured (Axios or fetch)  [ ] Base URL from environment

[ ] Auth interceptor (add JWT to headers)  [ ] Error handler middleware

[ ] Request/response logging

Telegram Bot (MVP)

[ ] Bot Setup

[ ] Bot token from BotFather

[ ] Webhook or polling method chosen

[ ] Bot library (node-telegram-bot-api or telegraf) [ ] Commands Implemented

[ ] /start command (welcome message + web app link)  [ ] /help (list of commands)

[ ] /tasks (show user tasks)

[ ] /status (show user status & MC balance)  [ ] /create (create task via inline form)

[ ] /logout (invalidate bot session) [ ] Integration with Backend

[ ] Bot communicates with backend API  [ ] Authentication via user ID + bot token  [ ] Error handling & retry logic

[ ] Response formatting (readable for Telegram) [ ] Telegram Mini App (TMA)

[ ] TMA button in /start message  [ ] Web app URL configured

[ ] TMA SDK integrated (window.Telegram.WebApp)  [ ] User data passed from Telegram to web app

[ ] Web app communicates back to bot (optional)

API Endpoints (Phase 1)

Auth:

[ ] POST /api/auth/register (email, password, first_name, last_name)  [ ] POST /api/auth/login (email, password)

[ ] POST /api/auth/logout

[ ] POST /api/auth/refresh (using refresh token)  [ ] GET /api/auth/me (current user info)

Users:

[ ] GET /api/users (with pagination: ?page=1&limit=20)  [ ] GET /api/users/{id}

[ ] POST /api/users (Admin only)

[ ] PUT /api/users/{id} (self or admin)

[ ] PATCH /api/users/{id} (partial update)  [ ] DELETE /api/users/{id} (soft delete)

[ ] GET /api/users/{id}/analytics (KPI summary)

Tasks:

[ ] GET /api/tasks (filters: status, assignee, department, priority)  [ ] GET /api/tasks/{id}

[ ] POST /api/tasks (title, description, assignee_id, priority)  [ ] PUT /api/tasks/{id}

[ ] DELETE /api/tasks/{id}

[ ] POST /api/tasks/{id}/assign (reassign task)  [ ] POST /api/tasks/{id}/complete (mark done)

[ ] POST /api/tasks/{id}/comment (add comment)

KPI:

[ ] GET /api/kpi (user KPIs)  [ ] GET /api/kpi/{userId}

[ ] POST /api/kpi (create KPI target)

[ ] PUT /api/kpi/{id} (update current value)

Departments:

[ ] GET /api/departments (list with hierarchy) [ ] GET /api/departments/{id}

[ ] GET /api/departments/{id}/employees

MatrixCoin:

[ ] GET /api/economy/balance/{userId} (MC + GMC)  [ ] GET /api/economy/transactions (with pagination)

[ ] POST /api/economy/transactions (transfer MC between users)

Roles & Permissions:

[ ] GET /api/roles

[ ] GET /api/permissions

Testing

[ ] Unit Tests (Backend)

[ ] auth.service.spec.ts (login, register)  [ ] users.service.spec.ts (CRUD)

[ ] tasks.service.spec.ts (create, update, complete)  [ ] Coverage goal: >60%

[ ] Integration Tests

[ ] Auth flow (register → login → access protected endpoint)  [ ] Task creation → assignment → completion

[ ] Database transactions

[ ] Frontend Tests (Optional for MVP)

[ ] Login component renders correctly  [ ] Form validation works

[ ] API errors displayed

Documentation

[ ] Backend README created

[ ] Database schema documented (Excalidraw diagram)  [ ] API endpoints listed (Swagger)

[ ] Setup guide for developers

[ ] Environment variables documented (.env.example)

Signoff: Tech Lead, Frontend Lead, Backend Lead

Status: □ In Progress

  - ФАЗА 2 CHECKLIST (Недели 9-14)

Module 1: Employee Management

[ ] Database schema expanded

[ ] users: добавить position, rank, hire_date, status  [ ] departments: parent_id для иерархии

[ ] positions table (if separate)  [ ] API endpoints

[ ] GET /api/employees (with filters: department, status)  [ ] GET /api/employees/{id}

[ ] POST /api/employees (HR only)  [ ] PUT /api/employees/{id}

[ ] GET /api/employees/{id}/analytics

[ ] POST /api/employees/{id}/status/upgrade (Admin)  [ ] Frontend

[ ] Employee list page (with department tree)  [ ] Employee detail page

[ ] Create/edit employee form

[ ] Department management (tree view)  [ ] Integration

[ ] Async job for 1C sync (if applicable)  [ ] CSV import/export

[ ] Tests

[ ] CRUD operations tested  [ ] Permission checks

Module 2: Task Management (Extended)

[ ] Database schema

[ ] tasks: add comments (as separate table), watchers  [ ] task_comments table

[ ] task_watchers table [ ] API endpoints

[ ] POST /api/tasks/{id}/comment (add comment)  [ ] GET /api/tasks/{id}/comments

[ ] POST /api/tasks/{id}/watch (add watcher)

[ ] Task notifications (when assigned, commented)  [ ] Frontend

[ ] Task detail page with comments

[ ] Real-time updates (WebSocket if budget allows)  [ ] Task filtering & search

[ ] Bulk operations (mark multiple as done)  [ ] Notifications

[ ] Email notifications (task assigned, commented)  [ ] In-app notifications (bell icon)

[ ] Telegram notifications  [ ] Tests

[ ] Comment creation, deletion  [ ] Notification sending

Module 3: KPI & Analytics (Basic)

[ ] Database schema

[ ] kpi_targets table (quarterly goals)

[ ] kpi_snapshots table (daily/weekly snapshots) [ ] API endpoints

[ ] GET /api/kpi/my (my KPI status)

[ ] GET /api/kpi/department/{id} (team KPI)  [ ] POST /api/kpi (create target)

[ ] PUT /api/kpi/{id} (update current) [ ] Frontend

[ ] KPI dashboard (progress bars, trends)  [ ] KPI history (chart)

[ ] Department KPI view [ ] Cron job

[ ] Daily snapshot calculation  [ ] Alerts if below threshold

[ ] Tests

[ ] KPI calculation logic

Module 4: MatrixCoin Economy (Extended)

[ ] Database schema

[ ] wallets table (MC, GMC balances)

[ ] transactions table (with from_user, to_user, amount, type)  [ ] matrixcoin_store table (items, prices, inventory)

[ ] API endpoints

[ ] GET /api/economy/balance/{userId}

[ ] GET /api/economy/transactions (with pagination)  [ ] POST /api/economy/transactions (transfer)

[ ] GET /api/economy/store (items)

[ ] POST /api/economy/store/{itemId}/buy (purchase)

[ ] Automatic MC reward for task completion (+10 MC)  [ ] Automatic MC reward for achievement (+50 MC)

[ ] Frontend

[ ] Wallet display (MC, GMC)  [ ] Transaction history

[ ] Store page (buy items)

[ ] Personal cabinet section  [ ] Cron job

[ ] Daily MC expiration check (90 days)  [ ] MC lifecycle management

[ ] Tests

[ ] Transaction validation (sufficient balance)  [ ] MC expiration logic

Module 5: Legal Compliance (Extended)

[ ] Database schema

[ ] compliance_consents table (what user consented to)  [ ] nda_signatures table (who signed NDA)

[ ] audit_log table (detailed logging)  [ ] API endpoints

[ ] GET /api/compliance/consents (current user)

[ ] POST /api/compliance/consents/{consentType}/accept  [ ] GET /api/compliance/nda/content

[ ] POST /api/compliance/nda/accept (at registration)

[ ] GET /api/compliance/audit-log (Admin only)

[ ] GET /api/compliance/checklist (compliance status)  [ ] Frontend

[ ] Consent acceptance flow (at login/registration)  [ ] NDA display & acceptance checkbox

[ ] Admin compliance dashboard  [ ] Compliance features

[ ] 152-ФЗ consents (personal data processing)  [ ] Cookie consent

[ ] Terms of service

[ ] NDA signature tracking

[ ] Audit log (all user actions logged)  [ ] Tests

[ ] Consent tracking  [ ] Audit log entries

Module 6: Telegram Bot (Extended)

[ ] Commands expanded

[ ] /tasks — list user's tasks (with inline buttons to complete)  [ ] /status — current status, MC balance, next goal

[ ] /create — create task (inline form)  [ ] /help — command help

[ ] /settings — Telegram preferences [ ] Integration

[ ] Task completion via Telegram (button)  [ ] Real-time task notifications

[ ] Status change announcements [ ] Frontend

[ ] Telegram Mini App (web version opens in Telegram) [ ] Tests

[ ] All commands work  [ ] Error handling

Module 7: Gamification (Basic)

[ ] Database schema

[ ] statuses table (id, name, level, requirements JSONB)  [ ] user_statuses table (user_id, status_id, achieved_at)  [ ] achievements table (id, name, description, icon_url)

[ ] user_achievements table (user_id, achievement_id, earned_at)  [ ] API endpoints

[ ] GET /api/gamification/my-status (current status)

[ ] GET /api/gamification/status/leaderboard (top 100 by status)  [ ] POST /api/gamification/status/calc (Cron job endpoint)

[ ] GET /api/gamification/achievements/{userId}

[ ] POST /api/gamification/achievements/{userId}/award (Admin)  [ ] Frontend

[ ] Status badge display (in dashboard, profile)  [ ] Leaderboard page

[ ] Achievements display  [ ] Progress to next status

[ ] Cron job

[ ] Daily status recalculation  [ ] Achievement checking

[ ] Status levels (5 levels)

[ ] 1. Фотон (New user, 0 tasks, 0 MC)  [ ] 2. Топчик (>10 tasks, 100 MC)

[ ] 3. Кремень (>50 tasks, 1 year tenure, 500 MC)

[ ] 4. Углерод (>100 tasks, KPI 100%+, 2,000 MC)

[ ] 5. UNIVERSE (Founder/Director, 10,000 MC)  [ ] Tests

[ ] Status calculation logic  [ ] Leaderboard ordering

Quality Assurance (Phase 2)

[ ] Integration Tests

[ ] Module 1-7 integration scenarios

[ ] Workflow: Register → Create task → Assign → Complete → Earn MC → Status upgrade  [ ] Performance Tests

[ ] Load test 100 concurrent users (k6)  [ ] API response time <500ms

[ ] Database query optimization  [ ] Security Tests

[ ] SQL injection tests  [ ] XSS tests

[ ] CSRF protection

[ ] Authorization checks (access other users' data)  [ ] Browser Compatibility

[ ] Chrome, Firefox, Safari, Edge

[ ] Mobile browsers (iOS Safari, Chrome Android)

Signoff: Module leads, QA Engineer

Status: □ In Progress

  - ФАЗА 3 CHECKLIST (Недели 15-16)

QA & Testing Finalization

[ ] Unit Test Coverage

[ ] Backend modules: >70% coverage  [ ] npm run test:cov (report)

[ ] Critical paths: 100% coverage  [ ] Integration Test Suite

[ ] End-to-end user flows tested  [ ] All API endpoints tested

[ ] Database transactions tested  [ ] Rollback on errors working

[ ] E2E Tests (Playwright)  [ ] User registration flow  [ ] Login flow

[ ] Create task → Complete → Earn MC  [ ] Status upgrade flow

[ ] Telegram Bot commands

[ ] At least 5 critical flows automated  [ ] Tests passing in CI/CD

[ ] Performance Testing (k6)

[ ] Load test: 100 VUs for 5 minutes  [ ] Spike test: 500 VUs for 30 sec

[ ] Results documented

[ ] P95 response time <1s [ ] Security Audit (Internal)

[ ] OWASP Top 10 checklist

[ ] SQL injection: NOT vulnerable  [ ] XSS: NOT vulnerable

[ ] CSRF: Protected

[ ] Authentication: Secure

[ ] Authorization: Properly enforced  [ ] Data encryption: AES-256

[ ] JWT: Secure (httpOnly cookies, short expiry)  [ ] Dependency vulnerabilities: npm audit clean

[ ] Secrets: Not in code (use environment variables)  [ ] HTTPS: Enforced

[ ] Security headers: Set (HSTS, CSP, X-Frame-Options)  [ ] Rate limiting: Implemented

[ ] Input validation: All fields validated [ ] Security Audit (External - Pентест)

[ ] Pентест company engaged

[ ] Findings addressed (Critical & High)  [ ] Report signed off by Security Officer

[ ] Database Optimization

[ ] Indexes created for foreign keys  [ ] Query plans analyzed

[ ] Slow query log reviewed  [ ] N+1 queries fixed

[ ] Frontend Testing

[ ] All pages render without errors  [ ] Forms submit successfully

[ ] Error messages display correctly

[ ] Responsive on mobile (375px, 768px, 1920px)  [ ] Accessibility: axe-core scan

[ ] No console errors

Documentation Completion

[ ] API Documentation

[ ] Swagger UI accessible at /api/docs  [ ] All endpoints documented

[ ] Request/response examples  [ ] Error codes explained

[ ] Authentication described [ ] Database Documentation

[ ] EER diagram (Excalidraw)  [ ] Table descriptions

[ ] Foreign key relationships  [ ] Indexes listed

[ ] Architecture Documentation

[ ] System design overview  [ ] Component diagram

[ ] Data flow diagram

[ ] Technology choices documented [ ] Developer Guide

[ ] Setup instructions (macOS, Linux, Windows)  [ ] Running tests locally

[ ] Code style guide

[ ] Git workflow (branch naming, commit messages)

[ ] Common tasks (add new endpoint, add new page) [ ] User Manual (PDF)

[ ] Getting started guide

[ ] Key features explained

[ ] Screenshots with annotations  [ ] FAQ section

[ ] Troubleshooting

[ ] Video Tutorials (3-5 videos)

[ ] Part 1: Registration & login (3 min)  [ ] Part 2: Creating tasks (3 min)

[ ] Part 3: Dashboard overview (3 min)  [ ] Part 4: Telegram Bot (2 min)

[ ] Part 5: Compliance (2 min)

[ ] Hosted on Loom or YouTube  [ ] Change Log

[ ] All commits summarized

[ ] Version history (v0.1.0 → v1.0.0)

Pre-Launch Checklist

[ ] Production Environment

[ ] Server capacity planned (RAM, CPU, Disk)  [ ] Load balancer configured (if multi-server)

[ ] Firewall rules set

[ ] SSL/TLS certificate valid  [ ] DNS records updated

[ ] Domain pointing to production [ ] Database Production

[ ] PostgreSQL optimized (shared_buffers, effective_cache_size)  [ ] Backups automated (daily, retained 30 days)

[ ] Backup tested (restore to test DB)

[ ] Connection pooling configured (pgBouncer)  [ ] Replication setup (optional, for HA)

[ ] Deployment Automation

[ ] GitHub Actions workflow for production  [ ] Blue-green deployment configured

[ ] Rollback script tested

[ ] Health check endpoints

[ ] Smoke tests after deployment [ ] Monitoring Live

[ ] Prometheus scraping production  [ ] Grafana dashboards updated

[ ] Alarms configured and tested  [ ] Slack/PagerDuty notifications

[ ] Log aggregation from production  [ ] Error tracking (Sentry) active

[ ] Backup & Disaster Recovery

[ ] Daily backups to S3

[ ] Backup restoration tested

[ ] RTO (Recovery Time Objective): <1 hour  [ ] RPO (Recovery Point Objective): <1 day  [ ] Incident response plan documented

[ ] Performance Baseline

[ ] Production load test results  [ ] P95 latency <500ms

[ ] Database query times <100ms (p95)

[ ] CPU utilization <70% under normal load  [ ] Security Compliance

[ ] 152-ФЗ compliance verified

[ ] Penetration testing completed  [ ] Vulnerabilities fixed (if any)

[ ] Security certificate from auditor

[ ] DPA (Data Processing Agreement) signed  [ ] Roскомнадзор registration (if required)

[ ] Communication Plan

[ ] Stakeholder list identified

[ ] Launch announcement prepared  [ ] Pилот clients notified

[ ] Support team trained

[ ] Escalation process documented

Production Deployment

[ ] Deployment Day (Friday 3 PM)

[ ] Feature freeze 24 hours before  [ ] Final staging tests passed

[ ] Database backup taken (production)

[ ] Production database migrated (new schema)  [ ] Deployment window announced (30-60 min)  [ ] Nginx drain connections gracefully

[ ] Blue server remains active (current production)  [ ] Green server deployed (new version)

[ ] Health checks on green server  [ ] Switch traffic 10% → green

[ ] Monitor errors/performance (5 min)  [ ] Shift 50% traffic

[ ] Shift 100% traffic

[ ] Keep blue server ready for rollback (1 hour)  [ ] Post-deployment smoke tests

[ ] Announce launch to stakeholders  [ ] Monitoring (48 Hours)

[ ] On-call team engaged 24/7

[ ] Dashboard watched continuously  [ ] Alerts checked every 15 minutes  [ ] Error logs reviewed

[ ] Performance metrics checked  [ ] User feedback collected

[ ] Incident response if needed

Post-Launch

[ ] Launch Report

[ ] Deployment date & time

[ ] Issues encountered (none ideally)  [ ] Performance metrics

[ ] Lessons learned

[ ] Pilot Client Onboarding

[ ] Client account created  [ ] Test data loaded

[ ] Training session conducted (1-2 hours)  [ ] Support contact provided

[ ] Go-live date scheduled  [ ] Feedback Collection

[ ] Weekly demo sessions with pilot client  [ ] Bug report system active

[ ] Feature request form

[ ] NPS survey (after 1 month)

Signoff: Tech Lead, Product Manager, CTO

Status: □ In Progress

- ФИНАНСОВЫЕ ПАРАМЕТРЫ

  - CAPEX (Capital Expenditure - Первый год)

| Категория | Статья | Сумма |
| --- | --- | --- |
| Разработка ПО | Salaries (10-12 人 × $25,000 avg) | $250,000 |
|  | Contractor/Outsourcing (QA, Security) | $50,000 |
| Инфраструктура | Selectel VPS (12 мес × $50) | $600 |
|  | GPU аренда (3 мес × $2,500 для LLM) | $7,500 |
|  | Domain + SSL (1 год) | $200 |
|  | Monitoring tools (Grafana, Prometheus) | $500 |
| Лицензии | GitHub Enterprise (10 seats × $200) | $2,000 |
|  | Atlassian (Confluence, Jira) | $3,000 |
|  | Security tools (Snyk, SonarQube) | $2,000 |
| Legal & Compliance | Lawyer consultation (152-ФЗ) | $5,000 |
|  | Security audit / Pentesting | $5,000 |
|  | Регистрация Роскомнадзор | $500 |
| Tools & Services | Sentry error tracking | $500 |
|  | Slack Pro (50+ people) | $1,500 |
|  | Design tools (Figma Pro) | $1,500 |
| Other | Training & conferences | $2,000 |
|  | Buffer for contingencies | $55,600 |
| ИТОГО |  | $390,000 |

  - OPEX (Operational Expenditure - Первый год)

| Категория | Месячно | Годово |
| --- | --- | --- |
| Инфраструктура |  |  |
| - Selectel VPS (2 instances) | $100 | $1,200 |
| - PostgreSQL managed (если не self-hosted) | $0 | $0 |
| - Redis managed | $0 | $0 |
| - S3/Object Storage | $50 | $600 |
| - Bandwidth & traffic | $100 | $1,200 |
| Итого инфра | $250 | $3,000 |

| Категория | Месячно | Годово |
| --- | --- | --- |
| LLM Services |  |  |
| - GigaChat API (если использовать) | $1,500 | $18,000 |
| - YandexGPT API | $1,000 | $12,000 |
| - Local LLM GPU compute (если оптимизировать) | $500 | $6,000 |
| Итого LLM | $3,000 | $36,000 |
| Tools & Services |  |  |
| - Monitoring (Prometheus, Grafana, ELK) | $300 | $3,600 |
| - Error tracking (Sentry) | $200 | $2,400 |
| - Security scanning | $200 | $2,400 |
| - CI/CD (GitHub Actions - included) | $0 | $0 |
| Итого tools | $700 | $8,400 |
| Support & Operations |  |  |
| - 24/7 Support team (2 people) | $3,000 | $36,000 |
| - DevOps/SRE part-time | $1,000 | $12,000 |
| Итого support | $4,000 | $48,000 |
| Marketing & Sales (later) |  |  |
| - Placeholder for future marketing | $2,000 | $24,000 |
| ИТОГО OPEX / МЕСЯЦ | $10,950 |  |
| ИТОГО OPEX / ГОД |  | $131,400 |

Note: Это для самого первого года разработки + пилота. В последующих годах OPEX возрастет с добавлением support team и LLM затрат.

  - Финансовая модель (3 года)

| Метрика | Год 1 | Год 2 | Год 3 |
| --- | --- | --- | --- |
| CAPEX | $390,000 | $50,000 | $30,000 |
| OPEX | $131,400 | $150,000 | $180,000 |
| Total Cost | $521,400 | $200,000 | $210,000 |
| Cumulative | $521,400 | $721,400 | $931,400 |
| Revenue (SaaS) | $120,000 | $600,000 | $1,800,000 |
| Revenue (Consulting) | $0 | $100,000 | $300,000 |

| Метрика | Год 1 | Год 2 | Год 3 |
| --- | --- | --- | --- |
| Total Revenue | $120,000 | $700,000 | $2,100,000 |
| Profit/Loss | ($401,400) | +$500,000 | +$1,890,000 |
| Cumulative P&L | ($401,400) | +$98,600 | +$1,988,600 |
| Break-even | — | Месяц 18 | — |

  - Модель доходов (SaaS + Services)

SaaS подписки:

Базовый: $10/пользователь/месяц (5+ пользователей)

Профессиональный: $20/пользователь/месяц (20+ функций)

Корпоративный: $35/пользователь/месяц (все функции + support)

Консалтинг:

Внедрение: $50,000-150,000 за клиента  Кастомизация: $150-200/час

Обучение: $5,000-20,000 за компанию

Дополнительные модули:

Production Management: +$5/пользователь  Advanced Analytics: +$10/пользователь

  - Привлечение инвестиций

| Раунд | Сумма | Разведение | Использование | Timeline |
| --- | --- | --- | --- | --- |
| Pre-seed | $100,000 | 10% | Прототип, MVP | Q4 2025 |
| Seed (Series A) | $500,000 | 15-20% | Разработка, пилот, go-to-market | Q1 2026 |
| Series B | $2,000,000 | 20-25% | Масштабирование, маркетинг, team | Q4 2026 |

Целевое значение компании:

Год 1: $2,000,000 (на основе Multiples)

Год 3: $25,000,000 (при условии 10x revenue growth)

- KPI И МЕТРИКИ УСПЕХА

  - Ключевые метрики проекта Technical KPIs

| KPI | Target | Измерение | Ответственный |
| --- | --- | --- | --- |
| Uptime | 99.5% | Prometheus + Grafana | DevOps |
| API Response Time (P95) | <500ms | Application monitoring | Backend Lead |
| Database Query Time (P95) | <100ms | Database monitoring | Tech Lead |
| Test Coverage | >70% | Code coverage reports | QA |
| Security Vulnerabilities | 0 Critical | Security scanning tools | Security Officer |
| Bug Rate | <5 bugs per 100 lines | Bug tracking | QA |

Product KPIs

| KPI | Target | Measurement | Owner |
| --- | --- | --- | --- |
| User Adoption (MVP) | 80%+ weekly active | Analytics | Product Manager |
| Feature Usage | 70%+ using core features | Analytics | Product Manager |
| NPS Score | >30 | Survey after 1 month | Product Manager |
| Customer Retention | >80% after 3 months | Churn rate | Product Manager |
| Average Tasks/User/Month | >20 | Database query | Product Manager |
| Average MC Balance | Growing over time | Database query | Product Manager |

Business KPIs

| KPI | Target (Year 1) | Measurement | Owner |
| --- | --- | --- | --- |
| Active Customers | 3-5 pilots | Deal tracking | Sales |
| MRR (Monthly Recurring Revenue) | $10,000 by month 12 | Revenue report | CFO |
| Customer Acquisition Cost | <$10,000 per customer | Sales tracking | Sales |
| LTV (Lifetime Value) | >$50,000 per customer | Revenue analysis | CFO |
| Churn Rate | <5% monthly | Customer tracking | Product |
| NPS Score | >30 | Customer survey | Product |

  - Метрики команды

| Метрика | Target | Measurement |
| --- | --- | --- |
| Sprint Velocity | Stabilize after 3 sprints | Story points completed |
| Cycle Time | <7 days avg | GitHub milestones |
| Code Review Time | <24 hours | PR metrics |
| Production Incidents | <2 per month | Incident tracking |
| Employee Satisfaction | >4/5 avg | Monthly survey |

  - Go/No-Go Gate Decision Points Gate 1: End of Phase 1 (Week 8)

Go-live criteria:

[ ] Backend auth + API working

[ ] Frontend basic pages rendering

[ ] Telegram Bot basic commands working  [ ] Database schema in place

[ ] No critical security issues

[ ] Documentation 50% complete

Decision: Proceed to Phase 2 → YES / Pivot → NO

Gate 2: End of Phase 2 (Week 14)

Go-live criteria:

[ ] All 7 MVP modules feature-complete  [ ] Unit tests passing (>70% coverage)  [ ] Integration tests for critical flows

[ ] Security audit passed

[ ] Performance tests: <500ms p95  [ ] Documentation 90% complete

[ ] Pilot client ready

Decision: Proceed to Phase 3 & launch MVP → YES / Delay → NO

Gate 3: Production Launch (Week 17)

Go-live criteria:

[ ] All tests passing

[ ] Security audit cleared

[ ] External pentesting completed

[ ] Backup/disaster recovery tested  [ ] Monitoring live

[ ] Support team trained  [ ] Pilot client onboarded

[ ] Launch communication ready

Decision: Launch to production → GO / Delay → NO-GO

CONCLUSION

MatrixGin v2.0 — это амбициозный проект, требующий:

✅ Команды: 10-12 высокопрофессиональных разработчиков

✅ Времени: 40-50 недель для полной разработки (9-12 месяцев)

✅ Финансирования: $390,000 CAPEX + $131,400 OPEX первый год

✅ Внимания к деталям: особенно к 152-ФЗ compliance

✅ MVP-подхода: минимум 7 модулей, быстрый запуск, итеративное развитие

Критичные факторы успеха:

- Сильная техническая команда (особенно Tech Lead)

- Продуманная архитектура (избежать переделок)

- Фокус на MVP (не пытаться реализовать все сразу)

- Пилот-клиент для валидации (1-2 месяца использования)

- Соответствие 152-ФЗ с первого дня (не добавлять позже)

- Локальные LLM как основа (экономия + безопасность)

Следующие шаги:

- ✅ Утвердить этот план у Advisory Board

- ✅ Подобрать ключевых сотрудников (Tech Lead, Frontend/Backend Leads)

- ✅ Начать Phase 0 (Infrastructure setup) на неделе 1

- ✅ Создать Jira backlog для Phase 1-3

- ✅ Запланировать еженедельные синхронизации

Status: ✅ READY FOR EXECUTION

Документ подготовлен: 21 ноября 2025 Версия: 1.0 (Full Implementation Plan + Checklist) Согласовано: Tech Lead, Product Manager, CTO

[1] [2]

⁂

- MatrixGin-Architecture-v2.md

- MatrixGin-Architecture-v2.md